## Task Break-Up
S.No | Activity | Sub Activity 1 | Sub Activity 2 | Resource | Remarks | Status | Time to Deploy Incremental functionality for testing
1 | Home Page design | At home page left side below four menu will be added . 1. JD Processing 2. Resume Processing 3. Matched Profile 4. Candidates details |  | Hem |  |  | At 10 AM
|  | On Heder Left corner: Pyramid Recruiter Dashboard will be displayed along with logo same as pyramid core. |  | Arpi
|  | In Footer, copyright thing need to be added |  | Arpi
2 | JD Processing | Interface to display all registered JD profile |  | Sarfaraz |  |  | At 11:30 PM
|  | Display the response of above interface in Grid when user will click on "JD Processing" Menu |  | Hem | Below would be in JD Grids column. ID(Hidden) JD Name Good to have Skills Mandatory Skills
|  | Upload JD from UI and render back JD profile in grid | One button "Upload JD" above the blank grid. | Hem
|  |  | Render response on UI in grid format along with pagination | Hem
|  | JD Processing Business Logic for upload URL | Fetch must have skills from JD | Diwakar
|  |  | Fetch good to have skills & load | Diwakar
|  |  | Populate JD model along with skill and load in tables | Diwakar | Will check if JD is already registered with same name then record will be modified instead insertion.
|  |  | Send already fetched must and good to have skills as a response to display on UI. | Diwakar
|  | Adhoch Modification of Job Profile on UI | On click of edit button recruiter can modify the soft skills and hard skills on the basis of JD_ID | Arpi
|  | Adhoc JD Update interface | Modify the and send it back to UI. | Sarfaraz
3 | Resume Processing | Interface to display all registered Candidate profile |  | Diwakar |  |  | At 1:00 PM
|  | Display the response of above interface in Grid when user will click on "Resume Processing" Menu |  | Hem | Below would be the columns on Candidate grid Candidate Name (First and Last Name) Email Phone Status (i.e. "Interview Scheduled", Pass, Fail, On-Hold, Offered, Offer Accepted) Due Date (Editable on click of edit button) Skills Shortlisted (Button) --Select due date first
|  | Upload Resume from UI and render back the Candidate profile in the grid | One button "Upload Resume" above the blank grid. | Arpi
|  |  | Render response of candidate profile on UI in grid format along with pagination | Arpi
|  | Resume Processing Business Logic for upload URL | Fetch candidates personal details | Sarfaraz
|  |  | Fetch candidates skills | Sarfaraz
|  |  | Populate candidate profiles model along with skill and load in the table | Sarfaraz | Will check if candidate is already there then will update the updated skills in to it.
|  |  | Send already fetched candidates profile details on UI to display. | Sarfaraz
4 | Matched Profile | Interface to display matched record once Menu Will click. |  | Diwakar |  |  | At 2:30 PM
|  | Create a UI where a table will be displayed with matched percentage. Candidate Name, Candidate ID (Hidden), JD Name, JD ID(Hidden), Skills Matched Percentage. ----User can select multiple records and hit shortlisted action | Display records with matched percentage | Hem
|  |  | Select one or multiple record and click on "Shortlist Button" | Hem
|  | Shortlist interface logic | Selecting shortlist button candidates will be marked shortlisted | Sarfaraz
|  |  | Send specific response to UI. | Sarfaraz
5 | Candidate Details | UI change: Once clicked all candidates get's displayed in table initially 10 along with pagination if candidates are registered. | TP1 & TP2, feedback text area would be there in Grid column. Once user will fill the result and hit save in respective row then data get saved. | Arpi | Below will be the column on Candidate Details grid: Candidate Name, M. No, email_id, Key Skills, TP1(Text Area), TP2(Text Area) Feedback, ,Status, IsJoined, Edit, Save,Schedule Meeting (Button-It will enable in that case only when interview is not scheduled) |  | At 4 PM
|  |  | One button "Schedule Meeting" would be present which will open meeting outlook page. | Arpi | Open a meeting invite .
|  |  | One column status need to be displayed. i.e. "Interview Scheduled", Pass, Fail, On-Hold, Offered, Offer Accepted | Arpi
|  |  | Is Joined column will also be there | Arpi
|  | Get all candidates profile to display in grid along with all columns values interface |  | Sarfaraz
|  | Save TP1 feedback interface |  | Diwakar
|  | Save TP2 feedback interface |  | Sarfaraz
6 | Database Design | Create schema and table structure. |  | Ashish
|  | Script to create tables |  | Ashish
7 | QA | Test Case creation |  | Vijay
|  | Automation Script |  | Vijay
|  | Test Case Execution |  | Vijay/Ashish | Ashish will help Vijay in test case execution
8 | Environment Setup | Create Git Repository |  | Diwakar |  | Done
|  | Install Eclipse |  | Diwakar |  | Done
|  | Install MySQL server in AWS |  | Diwakar |  | In-progress
|  | Install Visual C++ Redistributable |  | All
|  | Install MySQL Work Bench |  | All
|  | Install Git Client |  | All |  | Done for Diwakar
|  | Clone Repository |  | All
|  | Create feature branch to start their work |  | Diwakar/Sarfaraz/Hem/Arpi
|  | Install tomcat in local |  | Diwakar/Sarfaraz/Hem/Arpi
|  | AWS deployment, Spring Boot, .Net Service Bundle, Frontend Code, MySQL RDS |  | Diwakar | Everyone provide artefact Sarfaraj- .Net Bundle Hem - Frontend War file Diwakar- Jar file Ashish-DBSql script.